## Child Survival Action Plan
Child Survival Action Toolkit
TEXT IN RED is example from Sierra Leone, to be replaced
Sierra Leone Child Survival Action (CSA) Plan 2023-2025
| National Target (2025) | By 2025, reduce the under five mortality rate (U5MR) to less than 71 per 1000 live births
| Actions | Tasks | Milestones |  | 2025 Target
|  |  | 2023 | 2024
Bottleneck 1: Leadership and governance in Child Health at national and subnational levels, especially engagement and alignment of multiple stakeholders in child health inside and outside the government
Objective 1: Elevate Child Survival Action at the highest level for visibility and accountability
| 1. Create a Child Health Programme under RCH Directorate | Review Child Health governance and accountabilities within RCH directorate, across directorates/programmes and MoH leadership | Child Health Programme established by June 2023 and accountabilities clearly defined among all directorates | First annual performance review conducted based on JDs and TORs and feedback used to inform improvements | By 2025, a Child Health Programme at national level is functional with regular monitoring of progress for Child Survival
Establish manager and technical staff and clear TOR, including collaboration across directorates/programmes
|  | Develop costed annual workplan at national level across the MoHS departments | 2023 Annual workplan for Child Health finalized and communicated to district | 2024 Annual workplan for Child Health finalized and communicated to district
|  | Establish regular reporting mechanism on progress for Child Survival to Minister of Health | Monthly progress update on Child Survival to Senior Management (CMO/Executive Management Committee, UHC Core Team) | Monthly progress update on Child Survival to Senior Management (CMO/Executive Management Committee, UHC Core Team)
Develop a Child Health programme Monitoring and Evaluation Tool for midyear and annual performance tracking
| 2. Establish functional Child Survival coordination within the MoHS and with partners | Reconstitute Child Survival Technical Working Group with lead, secretariat, clear TORs with partners/MDAs | Child Survival coordination platform established |  | By 2025, a Child Survival coordination within MoHS, partners and MDAs is functional and effective
|  | Within MoHS: nominate Child Health Focal Points in key directorates/programmes with refined working relationships/areas of collaboration and joint workplan | Child Health Focal Points at national and sub-national levels nominated with clear TORs
|  | Increase efficiencies across all relevant directorates/progammes in MoHS: Child Health Programme, Quality Management Team (QMT), Directorates of Nutrition, PHC and NMCP to jointly plan for implementation activities (e.g. trainings, supervision, mentoring/coaching, stock monitoring etc.) | 2023/2024 annual work plan for Child Health Programme developed jointly with other directorates/programmes within and outside MoHS | Child Survival activities reflected in annual work plans of all directorates/programs in MoHS
|  | Leverage Child Survival TWG to strengthen coordination, collaboration and accountability around priorities for Child Survival: ensure donor and implementing partner/MDA activities are based on national priorities and plans | a) Monthly CS TWG meetings b) Partner plans on Child Survival aligned with MoHS at national level | a) Quarterly CS TWG b) Partner plans on Child Survival aligned MoHS at national level
| 3. Empower Child Health leadership at district level | Ensure districts are aware of national plans and priorities; optimize/align resources across programmes; and increase effective/ integrated implementation | CSA disseminated and popularized to all districts by Dec 2023
|  | Capacitate Child Health Focal Point (e.g. District Health Sister) at district level with clear job description/TOR to oversee implementation, monitoring and reporting; and to coordinate within DHMT and with medical superintendent | Child Health Focal Points nominated and capacitated in each district by Dec 2023 |  | By 2025, DHMT prioritize Child Survival activities in district work plans and budgets
|  | Strengthen Child Survival governance and coordination at district level (e.g. TWG or other) | 50% of districts with a functional MNCH TWG by Dec 2023 | 100% of districts with a functional MNCH TWG by Dec 2024
|  | Strengthen national-district coordination for Child Health: DMO to report progress for CSA at national level, covering the entire district | 50% of districts provide monthly progress reports and recommendations on CSA through DMO / CS focal person | 100% of districts provide monthly progress reports and recommendation on CSA through DMO / CS focal person
|  | Costed annual workplan for Child Survival implementation activities at district level | 2023 Annual workplans at districts capture Child Health activities as per the CSA | 2024 Annual workplans at districts capture Child Health activities as per the CSA
|  | Ensure partners implement the government priorities; and service level agreements are properly implemented | a) Monthly CS TWG meetings b) Partner plans on Child Survival aligned with 70% MoHS at district | a) Monthly CS TWG meetings b) Partner plans on Child Survival aligned with 100% MoHS at district
| 4. Optimize resource allocation and utilization for Child Survival | Regularly map key actors, resources (e.g. Child Survival TWG), and gaps; identify opportunities for optimized resource allocation; and track expenditures | Specific upcoming financing opportunities (Global Fund, Gavi FPP, World Bank, GFF, COVID-19, FCDO, USAID, UKAID, China AID, JICA, ISB, AfDB, others) to address joint priorities are targeted | 65% of CSA budget funded | By 2025, at least 80% of budgeted activities supporting Child Survival funded, with funding fully utilized
|  | Designated directorate to define and cost the PHC minimum package for delivery of integrated Child Health services | Essential health service package for UHC finalized and launched by Dec 2023 | Essential health service package for UHC implemented by Dec 2024
|  | Advocacy by Child Health Programme to Ministry of Health leadership for the inclusion of Child Survival actors in complete proposal development process for major funding opportunities | GF (NFM4, BIRCH, CR19), Gavi, FCDO, GFF, UKAID, China AID, USAID, IsB, AfDB, LAD portfolio plan contribute to key CSA priorities and support integrated delivery platforms
|  | Advocate for and allocate adequate resources to address Child Health priority activities at district level | 50% of Child Health priorities at district level adequately funded as reflected in district budgets by Dec 2023 | 100% of Child Health priorities at district level adequately funded as reflected in district budgets by Dec 2024
| 5. Advocacy for Child Survival Action | Develop and implement a national CSA advocacy plan/actions | Partners are aware and supportive of the CSA Plan |  | By 2025, champions and stakeholders support implementation of the CSA through advocacy
|  | Identify and empower high level/prominent champions (beyond the Minister of Health) | A champion is supporting advocacy for the CSA Plan by June 2023 | At least 2 champions are supporting advocacy for the CSA Plan by June 2024
|  | Identify and empower district and chiefdom level champions |  | District and chiefdom level champions are advocating for the CSA Plan by June 2024
|  | Advocate for resource allocation for child survival |  | Champions and stakeholders advocate for domestic financing and development funding for Child Survival
Bottleneck 2: ​Lack of quality data for child health, including accountability and oversight for reporting and use across all levels
Objective 2: Improve the collection, management and use of Child Health data at all levels
| 6. Strengthen data management system to generate evidence for Child Health | Strengthen Health Management Information System through selecting and integrating indicators related to Child Health (process/ outcome/ scorecard, etc.); consider incorporating qualitative data for experience of care | Critical Child Health/pediatric indicators are included in the DHIS-2 | Critical Child Health/pediatric indicators are reported | By 2025, the DHIS-2 is strengthened for Child Health and generates quality data which is analysed and used to improve the programme
| 7. Ensure quality of Child Health data | At national level, appoint M&E personnel in Child Health Programme to oversee quality of data and identify and act on bottlenecks, working with DPPI and other Directorates, as appropriate. | M&E personnel are appointed, trained, supported, and deployed in the Child Health Programme | Focal Points are identified and trained at facility level to support quality Child Health data
District to oversee the process of Child Health data collection in facilities including PHUs and community level, analysis and use towards strengthening Child Health service delivery
Identify and train a focal point in facilities including PHUs for RMNCAH data
| 8. Analyse and report/ feedback analysis to relevant stakeholders | Take actions through monthly data review meetings by the Child Health Programme Manager for key Child Health indicators, led by the RCH directorate to oversee Quality of Care and RMNCAH scorecard | Review analysis and feedback mechanism for data are strengthened | Review analysis and feedback mechanism for data are functional and regularly used
Quarterly Child Health Bulletin created by the directorate of RCH
Regular (monthly) review of district Child Health data in CHC, Hospitals and by DHMT (Revise the job description of DMO/ DHMT to include data analysis related to Child Health)
Quarterly joint review and feedback meetings at DHMT level (can be virtually) led by Child Health Focal Point
Bottleneck 3: Poor adherence to norms, standards, and guidelines for care at community, PHU and referral levels
Objective 3: Improve the quality of service delivery, especially HCW skills/competencies and quality improvement
| 9. Scale up and institutionalize quality improvement for integrated Child Health services across hospitals and to PHC level | National and district level jointly review key bottlenecks in the delivery of quality Child Health intervention packages (e.g. prevention, iCCM/IMNCI, CMAM etc.) for each level of care including community, PHU, hospital, including referral and back-referral. | Review meetings for bottlenecks in the delivery of Child intervention packages held and recommendations followed up | Review meetings for bottlenecks in the delivery of Child intervention packages held and recommendations followed up | By 2025, Quality of Care for Child Health intervention packages improves as measured by pediatric quality of care indicators
|  | Identify tracer indicators to measure progress in quality improvement of integrated Child Health and nutrition intervention packages (IMCI/iCCM, preventive package, ETAT, IMAM etc.) | Tracer indicators selected | Tracer indicators are reported on
|  | Revitalize and strengthen the use of the already established child death audit dashboard for improved decision making by the Child Health Programme | Child health death audits are used in all hospitals | Child health death audits are used in all hospitals, PHUs and community level
| 10. Scale up/intensify mentoring and coaching for integrated Child Health and nutrition interventions | Apply a common approach for standardized mentoring/coaching for Child Health interventions (based on national mentorship framework as well as best practices developed by in-country partners), including tools and scorecards to assess HCW competency against established pediatric QoC standards | Mentorshop approach and framework defined | Mentorship of HCWs undertaken | By 2025, mentoring and coaching is regularly undertaken and issues addressed to support quality Child Health interventions
|  | Provide quarterly supportive supervision for integrated Child Health interventions | Quarterly supportive supervision for Child Health interventions is undertaken | Quarterly supportive supervision for Child Health interventions is undertaken
| 11. Revise comprehensive pre-service training curriculum for Child Health | Engage with training institutions (Doctors, Nursing, CHWs etc.) to review and revise pre-service training to be adequate for delivery of Child Health and nutrition intervention packages (IMNCI/iCCM, ETAT, IMAM etc.) led by the Directorate of Training and supported by the Child Health Programme in collaboration with other relevant programmes/directorates and Child Survival TWG | Training institutions identified and engaged to revise pre-service training for Child Health intervention packages | Pre-service training curriculum is revised to include components of Child Health interventions | By 2025, revised pre-service training curriculum to include components of Child Health interventions is rolled out
| 12. Scale up integrated in-service training for key Child Health and nutrition interventions | Standardize training packages for Child Health/priority interventions, and develop a comprehensive training plan | Training packages for Child Health intervention packages are mapped and standardized | Comprehensive plan for training for integrated delivery platforms is finalized and costed | By 2025, in-service training database is in use and in-service training rolled out
|  | Establish of a database of HCWs trained in Child Health and nutrition interventions, map training needs and plan comprehensively for integrated delivery platforms (e.g. iCCM/IMNCI: Child Health, nutrition, NMCP and PHC) and ensure capacitated pool of trainers is available | Database established of trained HCWs | Pool of trainers for Child Health interventions is available
Bottleneck 4: Stockouts or unavailability of essential child health commodities at community, PHU, and referral levels
Objective 4: Improve visibility and ownership of quantification and stock monitoring of Child Health commodities, advocate with partners to support, and engage in distribution and monitoring of consumption
| 13. Ensure accountability for quantification, distribution and monitoring of use of essential Child Health commodities | Ensure regular monitoring of stocks of essential Child Health commodities at district level and report up to inform distribution, including: 1.Multi-stakeholder (programs & partners) quantification done at every facility; 2.Introduce a facility electronic monitoring system to capture data; and 3.Onsite storage, monitoring and verification of reporting for quality assurance and accountability | Complete quantification data for Child Health commodities is available from 50% of districts | Complete quantification data for Child Health commodities is available from all districts | By 2025, facilities are transitioned to more of a pull system relying on effective quantification, distribution and monitoring of essential Child Health commodities
|  | Child Health programme through RCH Directorate is engaged in National Supply Chain TWG and the TWG subsets | Regular engagement with National Supply Chain TWG for Child Health commodities | Regular engagement with National Supply Chain TWG for Child Health commodities
|  | Designate District Child Health Focal Points as a part of the existing Quantification TWG to oversee these efforts, identify and act on bottlenecks. | All essential Child Health commodities, beyond malaria, are included in Quantification TWG | All essential Child Health commodities, beyond malaria, are included in the annual quantification process
| 14. Ensure prioritization of Child Health commodities in all relevant procurements, both on-budget and in-kind | Include non-malaria commodities in the NFM 4 of GF: Quantify needs for non-malaria commodities in iCCM to be included in GF proposal (Gap analysis). Ensure designated focal point in MoHS to lead on this effort. | GF proposal developed and submitted by June 2023, including non-malaria commodities | Non-malaria commodities supported through Global Fund procured and reaching CHWs | By 2025, Child Health commodities are funded at all levels
|  | Prioritize Child Health commodities in potential new funding opportunities | Potential funding opportunities for inclusion of Child Health commodities are identified | Proposals are written to include Child Health commodities
|  | Advocate for cost recovery scheme (drug revolving fund)/SLeSHI in facilities so that Child Health commodities are made available. Inclusion of child health commodities in existing cost recovery scheme at tertiary hospitals | Child Health commodities are included in ongoing procurement, policy, and financial frameworks for cost recovery scheme/SLeSHI | Cost recovery scheme/SLeSHI with inclusion of Child Health commodities is rolled out
|  | Strengthen visibility (e.g. dashboard) of what is procured and distributed, including quantification at national and district level for Child Health commodities, based on the data from the DHIS-2 and Event Management tool | Dashboard is used for alerting RCH of gaps in Child Health commodities | Dashboard is used for alerting RCH of gaps in Child Health commodities
|  | Leverage recent and ongoing medical oxygen investments, to ensure availability of appropriate equipment and clinical capacity for hypoxemia management in children |  | Medical oxygen investments are available at CHCs to support children
| 15. Strengthen distribution by decentralizing the process from district to facilities and CHWs | District to complement the distribution function of NMSA using local government resources/allocated resources for last mile distribution, focused on redistribution/resupply (reverse logistics) to facilities between quarterly distributions | Plans developed for redistribution/resupply of Child Health commodities to facilities between quarterly distributions | Redistribution/resupply of Child Health commodities is done for 50% of facilities between quarterly distributions | By 2025, Child Health commodities are available at the facility and community level including the last mile
|  | Orient district pharmacists and partners about the use of data to inform the allocation of drugs and supplies for iCCM, IMNCI and first level referral care | Orientation for district pharmacists about the use of data is undertaken | District pharmacists are using data to inform allocation and distribution of Child Health commodities
|  | Ensure both PHUs and CHWs are equipped/don’t have stockouts of essential Child Health commodities (e.g. pre-pack for CHWs pending completion of ongoing pilot) | Findings from pilot of pre-pack for CHWs in hard-to-reach areas are used ensure CHWs have Child Health Commodities | Ensure 100% of CHWs in hard-to-reach-areas have Child Health commodities available
Bottleneck 5: ​Inadequate community outreach and services to promote care-seeking, prevent childhood illnesses, and treat children in hard-to-reach areas
Objective 5: Ensure all children in hard-to-reach areas can access iCCM, and preventive/promotive health and nutrition interventions implemented by CHWs
| 16. Intensify health education and advocacy with communities, connected to ongoing and strengthened campaigns, including amplification by CHWs | Support the operationalization of the SBCC strategy for RMNCAH, including review of Child Health specific messages | SBCC strategy is reviewed for inclusion of Child Health specific messages | Develop Child Health specific messages as necessary | By 2025, caregivers of children in hard-to-reach areas are reached with Child Health specific messages
|  | Engage at the community level through intensified messages, community engagement meetings, and feedback with stakeholders such as local councils, chiefs, civil society organizations, religious leaders, tribal leads, traditional healers, facility management committees (FMC), village development councils (VDCs), ward committees, town criers, and mother support groups | Health Education Department is engaged to support Child Health interventions | Intensified messages and engagement with community stakeholders are regularly undertaken
|  | Support and strengthen campaigns (e.g. Immunization Day, Child Health Weeks, etc.) | Child Health specific messages are regularly included in campaigns | Child Health specific messages are regularly included in campaigns
|  | Ensure promotional and preventive Child Health messages (e.g. sanitation and hygiene promotion, care-seeking, immnuziation) are part of CHW amplification at community level | Child Health specific messages are reviewed in CHW package | Child Health specific messages are strengthened in CHW package
| 17. Improve PHU support for CHWs | Plan, monitor, supply and support monthly meetings of PHU in-charge with CHWs | Monthly meetings of PHU in-charge with CHWs are undertaken | Number of communities and children reached by CHWs is increased | By 2025, PHU support to CHWs is strengthened
|  | Strengthen Supervision, partner audits, work with district leaders, partnerships in supervision | Supervision and partner audits are undertaken | Supervision and partner audits are undertaken
| 18. Strengthen home visits by CHWs and other community-level agents (e.g. WASH, Agriculture), leveraging multi-sector engagement at community level | Improve CHWs' ability to undertake home visits (e.g. procurement of bicycles, motorbikes, transport refund) through community health focused grants (e.g. Global Fund) | Proposals submitted for potential funding opportunities (e.g. Global Fund) to support for CHWs to undertake home visits | CHWs in hard-to-reach area are supported to undertake home visits | By 2025, children in hard to reach areas receive quality curative, preventive, promotive and treatment services
| 19. Strengthen systems of accountability, especially community feedback | Improve the use of client chatters, radio programs, community radio, and community scorecard | Pilot Community Scorecard in 2 districts | Community Scorecard is scaled up among the districts | By 2025, the Community Scorecard is used in all districts
Bottleneck 6: Actual and potential role of private sector providers is not fully exploited
Objective 6: Understand the role of and ways to better engage private sector for delivery of essential Child Health services
| 20. Build capacity of private providers in diagnosis and treatment of childhood illness according to national guidelines | Understand the role and map private providers in diagnosis and management of Child Health services | Establish MOU between MoHS and association of private sector providers to ensure accountability, sharing of data, knowledge sharing, and use of guidelines and tools | Mapping of private providers is completed and guidelines are established | By 2025, relevant public private partnership MOU, SOP and guidelines are developed
Work with private provider associations/representatives on how to engage private providers in capacity building efforts
Provide training for selected private providers on Child Health services
| 21. Use private sector as a partern in filling child health service delivery gaps | Establish system of referral and service provision from public facilities to private hospitals, when care cannot be provided (e.g. stockout of key commodities) | Child Health to work with relevant directorate in MoHS to engage on public private partnership
|  | Strengthen innovations that could support child health, such as telemedicine, through possible public-private partnership |  | Mapping and planning for innovations with private sector is completed
MoH logo